## Sheet1
# Week | Task Module | Features to be implemented | Activities to be done | App Dev (man-hour) | Start Date | End Date | Module Total (man-month)
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understand the purpose, scope, and objectives of the trainee selection system | 4 | 2023-07-03 | 2023-07-03
|  |  | 1.1.2 Develop project schedule | 2 | 2023-07-03 | 2023-07-03
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-07-03 | 2023-07-03
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-07-04 | 2023-07-04
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-07-04 | 2023-07-04
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-07-04 | 2023-07-05
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-07-05 | 2023-07-05
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-07-05 | 2023-07-06
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-07-06 | 2023-07-06
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-07-07 | 2023-07-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-07 | 2023-07-07
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze user registration API | 2 | 2023-07-08 | 2023-07-08
|  |  | 2.1.2 Analyze application submission API | 2 | 2023-07-08 | 2023-07-08
|  |  | 2.1.3 Analyze application status API | 2 | 2023-07-08 | 2023-07-08
|  |  | 2.1.4 Analyze circular creation API | 2 | 2023-07-08 | 2023-07-08
|  |  | 2.1.5 Analyze review applications API | 2 | 2023-07-09 | 2023-07-09
|  |  | 2.1.6 Analyze approve trainees API | 2 | 2023-07-09 | 2023-07-09
|  |  | 2.1.7 Analyze admit card generation API | 2 | 2023-07-09 | 2023-07-09
|  |  | 2.1.8 Prepare documentation about API responses | 4 | 2023-07-10 | 2023-08-10
|  | 2.2 Design User Interface (UI) | 2.2.1 Design registration/login page | 4 | 2023-07-10 | 2023-07-11
|  |  | 2.2.2 Design circular form | 4 | 2023-07-11 | 2023-07-12
|  |  | 2.2.3 Design application submission form | 4 | 2023-07-12 | 2023-07-12
|  |  | 2.2.4 Design dashboard/noticeboard page or lists/table to display application statuses or trainee information | 4 | 2023-07-13 | 2023-07-13
|  |  | 2.2.5 Design applicants profile page | 4 | 2023-07-13 | 2023-07-13
|  |  | 2.2.6 Design page for uploading marks | 4 | 2023-07-13 | 2023-07-13
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 2023-07-14 | 2023-07-14
|  |  | 2.3.2 Analyze relationship between entities | 8 | 2023-07-14 | 2023-07-14
3 | Development
|  | 3.3 User Registration and Authentication | 3.3.1 Implement the functionality for user registration | 2 | 2023-07-15 | 2023-07-15
|  |  | 3.3.2 Capturing user information | 2 | 2023-07-15 | 2023-07-15
|  |  | 3.3.3 Validating user credentials | 2 | 2023-07-16 | 2023-07-16
|  |  | 3.3.4 Implement secure user authentication mechanisms | 2 | 2023-07-17 | 2023-07-17
|  | 3.4 Trainee Application Management | 3.4.1 Implement the functionality for trainees to submit their applications | 2 | 2023-07-17 | 2023-07-17
|  |  | 3.4.2 Validate and store trainee application data | 2 | 2023-07-18 | 2023-07-18
|  | 3.5 Admin Panel and Applicant Approval | 3.5.1 Develop an admin panel for reviewing and approving trainee applications | 2 | 2023-07-18 | 2023-07-18
|  |  | 3.5.2 Implement the functionality for admin to review and mark trainee applications as approved | 2 | 2023-07-19 | 2023-07-19
|  | 3.6 Admit Card Generation and Tracking | 3.6.1 Implement the functionality to generate unique admit cards for selected trainees | 2 | 2023-07-19 | 2023-07-20
|  |  | 3.6.2 Develop tracking mechanisms to monitor the progress and status of trainee applications | 2 | 2023-07-20 | 2023-07-20
|  | 3.7 Evaluation and Marking | 3.7.1 Design evaluation criteria and mark trainee applications based on specified criteria | 2 | 2023-07-20 | 2023-07-21
|  |  | 3.7.2 Implement the functionality for evaluators to upload and submit marks for trainee applications | 2 | 2023-07-21 | 2023-07-21
|  | 3.8 Notification and Communication | 3.8.1 Implement an internal mailing system for sending notifications to trainees regarding their application status | 2 | 2023-07-21 | 2023-07-21
|  |  | 3.8.2 Develop a trainee dashboard or notice board to display important notices and updates | 2 | 2023-07-22 | 2023-07-22
|  | 3.8 Reporting and Result Preparation | 3.9.1 Implement the functionality to generate reports and prepare the final list of selected trainees | 4 | 2023-07-22 | 2023-07-22
4 | Quality Assurance and Project closing
|  | 4.1 Software testing and quality assurance | 4.1.1 Develop test cases and conduct thorough testing of the trainee selection system | 8 | 2023-07-23 | 2023-07-23
|  |  | 4.1.2 Perform quality assurance activities and address any identified issues or bugs | 4 | 2023-07-23 | 2023-07-23
|  |  | 4.1.3 Fix bugs and defects | 2 | 2023-07-24 | 2023-07-24
|  | 4.2 Project closing | 4.2.1 Prepare the deployment checklist and deploy the trainee selection system to the production environment | 4 | 2023-07-25 | 2023-07-25
|  |  | 4.2.2 Review and finalize all project-related documentation | 4 | 2023-07-25 | 2023-07-25
150